## Project Proposal
Project Proposal: Wholistic Health App
Company Name:
Contact Name:
Contact Email:
Contact Phone:
Projected Dates:
You may request and utilize the requirements document to provide an accurate and comprehensive quote.
[5 empty] | Period Highlight: |  | 0
Milestone | Planned Start | Planned Duration | Actual Start | Actual Duration | Cost | % Complete | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
WEEK
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Login (Individual) | 1 | 5 |  |  |  | 0%
Information | 3 | 6 |  |  |  | 0%
Enter Results | 4 | 4 |  |  |  | 0%
View Results | 5 | 8 |  |  |  | 0%
Create Plan | 6 | 2 |  |  |  | 0%
Edit Plan | 7 | 3 |  |  |  | 0%
Link / Unlink Your Profile to a Provider | 10 | 4 |  |  |  | 0%
Individual Reports | 12 | 2 |  |  |  | 0%
Learn More (Individual) | 15 | 2 |  |  |  | 0%
Login (Professional) | 17 | 5 |  |  |  | 0%
List of Patients / Clients | 18 | 1 |  |  |  | 0%
Create Health Provider Account | 19 | 3 |  |  |  | 0%
Provider Payment Options | 20 | 8 |  |  |  | 0%
User Information for Providers | 21 | 3 |  |  |  | 0%
Provider Payment Options | 22 | 4 |  |  |  | 0%
Edit Departments, Programs / Units, Teams, and CPs | 23 | 5 |  |  |  | 0%
Professional / Provider Reports | 23 | 2 |  |  |  | 0%
Learn More (Provider / CP) | 23 | 6 |  |  |  | 0%
Add Another Milestone and Cost You Think is Needed | 14 | 8 |  |  |  | 0%
Add Another Milestone and Cost You Think is Needed | 14 | 7 |  |  |  | 0%
Add Another Milestone and Cost You Think is Needed | 15 | 4 |  |  |  | 0%
Add Another Milestone and Cost You Think is Needed | 15 | 5 |  |  |  | 0%
Add Another Milestone and Cost You Think is Needed | 16 | 28 |  |  |  | 0%
|  |  |  | Total Cost | 0